## By People
Person | Question | Week: 11-15/03/19
|  | Monday (S.M - Mai) | Tuesday (S.M - David) | Wednesday (S.M - Wes) | Thursday (S.M - Terry) | Friday (S.M - Alan)
Mai | What did you do yesterday? | Provisional research | Familiarized with HEAT | Finalise design phase | Setup Gitlab | Continued setting up Wiki layout and editing structure and content. Assigning documenting tasks to group members.
| What will you work on today? | Familiarize with HEAT, user stories | Requirements editing, customer interviews | Setup Gitlab | Feature layout, restructured wiki layout, develop content for development process and features documentation | Organizing sprint introspective and sprint review
| Do you have any obstacles? | Potentially with the software | Many potential requirements | Unfamiliar with Gitlab | Gitlab is hard to navigate | No
Alan | What did you do yesterday? | Provisional research | Familiarized with HEAT | Experiment with code changes, background research and began looking into colour changes | Make colour/contrast changes in code | Resolved merge conflicts between two brances, user testing and implemented changes based on feedback. Started documentation.
| What will you work on today? | Familiarize with HEAT | Requirements research, experiment with code changes | Continue investigating colour changes | Finish code implementation and make final commits | Continue work on documentation. Continue testing.
| Do you have any obstacles? | Potentially with the software | Vastness of code | Colour related code implemented in several different places | Difficulties with merging on git | Document merging conflicts.
Wes | What did you do yesterday? | Provisional research | Familiarized with HEAT | Experiment with code changes, background research and began looking into sound effects and cursor changes | Implemented sound effects for success and failure and increase cursor size and design | Created a new mouse class and mouse images.
| What will you work on today? | Familiarize with HEAT | Requirements research, experiment with code changes | Continue investigating sound effects and cursor changes | Started mouse class. | Fixing issues with the new mouse class. Made changes based on user testing feedback. Fixing mac compatibility issue.
| Do you have any obstacles? | Potentially with the software | Vastness of code | Code spread out across a number of classes, had to do a lot of research how Jframe works, HEAT private methods | Locating appropriate areas to put code. Finding the classes than needed to be utilized. | Finding the correct position for the cursor change.
David | What did you do yesterday? | Provisional research, user stories | Familiarized with HEAT | Background research and began looking into font size and type | Changed font sizes within majority of application areas | Unit testing and defect fixes.
| What will you work on today? | Familiarize with HEAT | Background research, experiment with code changes | Continue investigating font size and types | Finish code implementation and make final commits, updated Wiki with background research, features and tools. | Final report, tools and implementation, development testing and review documentation
| Do you have any obstacles? | Potentially with the software | Vastness of code | Font code located in many different classes within the program | Difficulties with merging on git | A few elements require additional research and java knowledge to implement changes.
Terry | What did you do yesterday? | Provisional research | Familiarized with HEAT | User stories, customer interview | UML diagrams, acceptance criteria documentation | Wrote tests and delegated testing tasks.
| What will you work on today? | Familiarize with HEAT, user stories | Requirements editing, customer interviews | UML diagrams | Writing test planning and strategy | Documentation and proof-reading
| Do you have any obstacles? | Potentially with the software | Many potential requirements | User case diagram must convey two different types of user, class diagram is complicated in structure | Writing tests for all new features will be extensive | Lots of documentation to proof-read and gather

## By Questions
Question | Person | Week: <date>
|  | Monday | Tuesday | Wednesday | Thursday | Friday
What did you do yesterday? | Jane
Alex
Jessica
What will you work on today? | Jane
Alex
Jessica
Do you have any obstacles? | Jane
Alex
Jessica